## front
S NO. | SEVERITY | PRIORITY | Assign To | PAGE | STATUS | SUMMARY | URL | DATE CREATED | Comments
Admin Panel
1 | high | high | daniyal | Goods Owner List | open | edit and delete function not working | http://lorrynlorry.xolva.com/admin/goods_list.php?param=1# | 2019-11-22
2 | high | high | daniyal | Goods Owner List | open | UI issue while using detail button on Goods Owner List | http://lorrynlorry.xolva.com/admin/goods_list.php?param=1# | 2019-11-22
3 | low | low | daniyal | Goods Owner Registration | open | Textual error in Goods Owner field | http://lorrynlorry.xolva.com/admin/goods_owner_registration.php | 2019-11-22
4 | high | high | daniyal | Goods Owner Registration | open | No validations or mendetory field in form (form is proceeding without any information)/numeric and alphabetic character validation | http://lorrynlorry.xolva.com/admin/goods_owner_registration.php | 2019-11-22
5 | high | high | daniyal | Documents Required (goods owner) | open | error on submit button | http://lorrynlorry.xolva.com/admin/owner_type.php?param=28 | 2019-11-22
6 | high | high | daniyal | Lorry Owner Registration | open | No validations or mendetory field in form (form is proceeding without any information) | http://lorrynlorry.xolva.com/admin/owner_registration.php | 2019-11-22
7 | high | high | daniyal | Documents Required (lorry) | open | error on submit button | http://lorrynlorry.xolva.com/admin/owner_type.php?param=34 | 2019-11-22
8 | high | high | daniyal | Lorry Owner List | open | edit and delete function not working | http://lorrynlorry.xolva.com/admin/owner_list.php# | 2019-11-22
9 | high | high | daniyal | Lorry Owner List | open | UI issue while using detail button on lorry owner List | http://lorrynlorry.xolva.com/admin/owner_list.php# | 2019-11-22
10 | high | high | daniyal | Driver List | open | edit and delete function not working | http://lorrynlorry.xolva.com/admin/driver_list.php | 2019-11-22
11 | high | high | daniyal | Driver List | open | UI issue while using detail button on driver List | http://lorrynlorry.xolva.com/admin/driver_list.php | 2019-11-22
12 | high | high | daniyal | Driver List | open | No validations or mendetory field in form (form is proceeding without any information)/numeric and alphabetic character validation | http://lorrynlorry.xolva.com/admin/driver_registration.php | 2019-11-22
13 | high | high | daniyal | Truck List | open | UI issue while using detail button on driver List | http://lorrynlorry.xolva.com/admin/truck_list.php | 2019-11-22
14 | high | high | daniyal | Add New Truck | open | No validations or mendetory field in form (form is proceeding without any information)/numeric and alphabetic character validation | http://lorrynlorry.xolva.com/admin/truck_add.php | 2019-11-22
15 | high | high | daniyal | Add New Truck | open | truck name, id , load capacity,track id,model,made by, all detail should be correct as filled in form. | http://lorrynlorry.xolva.com/admin/truck_add.php | 2019-11-22
16 | high | high | daniyal | all forms in admin portal | open | file upload indication missing in all forms(no signs for uploaded files) |  | 2019-11-22
17 | high | high | daniyal | Load Post List |  | Ui disturbed on detail button | http://lorrynlorry.xolva.com/admin/load_post_list.php | 2019-11-22
Goods Owner Panel
17 | high | high | daniyal | New Job Post | open | No validations or mendetory field in form (numeric and alphabetic character validation) | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | not done
18 | high | high | daniyal | Pending Jobs List | open | delete and edit button not working | http://lorrynlorry.xolva.com/goodsowner/load_list.php | 2019-11-29 | ignore
19 | high | high | daniyal | New Job Post | open | UI Disturbed/syntax error/logout button missing…….. Find the screenshot attached/ home button not working | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | done
20 | high | high | daniyal | New Job Post | open | Date SelectorS in form should not select previous date | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | done
21 | high | high | daniyal | New Job Post | open | no of container should not accept minus value | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | done
22 | high | high | daniyal | New Job Post | open | no of truck should not be in minus | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | done
23 | high | high | daniyal | New Job Post | open | agent mobile num should be customized. | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | done
24 | high | high | daniyal | Pending Jobs List | open | UI issue while using detail button | http://lorrynlorry.xolva.com/goodsowner/load_list.php | 2019-11-29 | done
25 | high | high | daniyal | Bid List | open | logout botton not avaliable | http://lorrynlorry.xolva.com/goodsowner/bidding_list.php# | 2019-11-29 | not done
26 | high | high | daniyal | New Job Post | open | form error: form is accepting incorrect information like minus values, alphabet instead of numeric and numeric instead of alphabet | http://lorrynlorry.xolva.com/goodsowner/add_load.php | 2019-11-29 | not done
27 | high | high | daniyal | all pages | open | all links in control panel should open in new tab | http://lorrynlorry.xolva.com/goodsowner/index.php | 2019-11-29 | not done
28 | high | high | daniyal | Complete Jobs | open | error in destination detail button | http://lorrynlorry.xolva.com/goodsowner/complete_job.php | 30/12/19 | ???
29 | high | high | daniyal | Jobs Image List | open | image list allignment | http://lorrynlorry.xolva.com/goodsowner/complete_images.php?load_id=49 | 30/12/19 | ???

## Article by disease (hidden)
S NO. | SEVERITY | PRIORITY | PAGE | STATUS | SUMMARY | URL | DATE CREATED
1 | minor | high | Article by Disease | open | In drop down of article by disease by selecting view all article by disease page open in which images are not displaying. | http://beta.eurekaselect.com/alldiseases | 28-8-2019
2 | minor | high | Anti Inflammatory | open | Textual errors : not proper formating of alphabets and sub diseases list is not in alphabetic order. | http://beta.eurekaselect.com/alldiseases/295/anti%20inflammatory | 28-8-2019
3 | minor | high | Cardiovascular Disorders | open | Textual errors : sub diseases list is not in alphabetic order and a cross (x) is appearing on the title/heading of Bentham Cardiovascular Disorders Collection. | http://beta.eurekaselect.com/alldiseases/258/cardiovascular%20disorders | 28-8-2019
4 | minor | high | Central Nervous System | open | Textual errors : sub diseases list is not in alphabetic order and a cross (x) is appearing on the title/heading of Bentham Central Nervous System Collection. | http://beta.eurekaselect.com/alldiseases/281/central%20nervous%20system | 28-8-2019
5 | minor | moderate | Diabetes | open | A small image icon is appearing on the title/heading of Bentham Diabetes Collection. | http://beta.eurekaselect.com/alldiseases/283/diabetes | 28-8-2019
6 | minor | moderate | Oncology | open | A small image icon is appearing on the title/heading of Bentham Oncology Collection. | http://beta.eurekaselect.com/alldiseases/16/oncolo | 28-8-2019